## Foundations of Transfer Learnin
Artifact | Video Name | Development Status | Recording Status | Drive upload | Reviewer | Review | Planned Date | Completion Date | Final Review on LMS | Remarks
MODULE 1: Python and Machine Learning Fundamentals
Lesson 1.1: Python Environment Setup and Essentials
Video | Course Introduction |  |  | FALSE |  | FALSE
Video | Python: Backbone of Machine Learning | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Setting Up VS Code | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Python Fundamentals for Machine Learning | Completed | Completed | TRUE |  | FALSE
Reading | Python ML Environment Setup Guide: Conda, pip, and Jupyter Best Practices |  |  | FALSE |  | FALSE
Ungraded Assignment | Practice Knowledge Check: Python Environment and Essentials |  |  | FALSE |  | FALSE
Lesson 1.2: NumPy, Pandas, and Data Visualization
Video | Preparing Data for Machine Learning | Completed | Completed | FALSE |  | FALSE
Video | Hands On: NumPy Arrays and Vectorized Operations | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Pandas for ML Data Handling (attach iris.csv dataset) | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Data Visualization with Matplotlib and Seaborn | Completed | Completed | FALSE |  | FALSE
Reading | NumPy and Pandas Reference Guide for Machine Learning Practitioners |  |  | FALSE |  | FALSE
Ungraded Assignment | Practice Knowledge Check: NumPy, Pandas, and Visualization |  |  | FALSE |  | FALSE
Lesson 1.3: Machine Learning Fundamentals
Video | Decoding Machine Learning: Core Concepts and Insights | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Building Your First Machine Learning Model | Completed | Completed | TRUE
Video | Hands-On Evaluation of Machine Learning Models | Completed | Completed | TRUE
Reading | Core Machine Learning Concepts: A Practitioner's Reference
Ungraded Assignment | Practice Knowledge Check: Machine Learning Fundamentals
Reading | Module Summary
Graded Assignment | Knowledge Check: Python and Machine Learning Fundamentals
MODULE 2: Neural Networks and Transfer Learning Principles
Lesson 2.1: How Neural Networks Learn
Video | How Neural Networks Learn | Completed | Completed | TRUE
Video | Neural Network Training Pipelines | Completed | Completed | TRUE
Video | Hands-On: Building a Neural Network using NumPy | Completed | Completed | TRUE | [5 empty] | Y
Video | Hands-On: Neural Network Training Lab with PyTorch | Completed | Completed | TRUE
Reading | Neural Networks: From Perceptrons to Deep Learning
Ungraded Assignment | Practice Knowledge Check: How Neural Networks Learn
Lesson 2.2: Deep Learning and Feature Hierarchies
Video | Convolutional Neural Networks Architecture Basics | Completed | Completed
Video | Hands-On: CNN Feature Visualization Lab | Completed | Completed
Video | Recurrent Neural Networks and Backpropagation | Completed | Completed
Video | Hands-On: Embedding Spaces Visualized: Plotting Word2Vec and BERT Embeddings with t-SNE and Interpreting Geometric Meaning | Completed
Reading | RNN reading
Ungraded Assignment | Practice Knowledge Check: Deep Learning and Feature Hierarchies
Lesson 2.3: Transfer Learning: Principles and Strategies
Video | Transfer Learning Defined/ Transfer Learning: The Foundation of Modern AI | In Progress |  | FALSE | FALSE | FALSE
Video | Hands-On: Transfer vs Training from Scratch | In Progress
Video | Hands-On: Transfer Strategy Decision Lab / Choosing the Right Transfer Strategy | Completed
Video | Hands-On: Navigating the Hugging Face Hub for Model Selection | Completed
Reading | Transfer Learning Strategies and Use Cases: A Practitioner's Framework
Ungraded Assignment | Practice Knowledge Check: Transfer Learning Principles and Strategies
Reading | Module Summary
Graded Assignment | Knowledge Check: Neural Networks and Transfer Learning Principles
MODULE 3: Task Formulation and Dataset Preparation
Lesson 3.1: Task Formulation and Label Engineering
Video | Task Formulation in machine learning | Completed
Video | Hands-On: Task Formulation Lab: Converting a Customer Churn Problem into Binary Classification — Features, Labels, and Task Definition Walkthrough | Completed
Video | Hands-On: Label Engineering for Fine-Tuning: Building Multi-Class Labels, Instruction-Response Pairs, and Sequence Tags from Raw Data | Completed
Reading | Task Design Patterns for Transfer Learning and Fine-Tuning
Ungraded Assignment | Practice Knowledge Check: Task Formulation and Label Engineering
Lesson 3.2: Dataset Cleaning, Tokenization, and Splitting
Video | Data Engineering for ML: Why Data Quality Determines Model Quality — Noise, Duplicates, Imbalance, Leakage, and the Right Data Split Strategy
Video | Hands-On: Dataset Cleaning Lab: Detecting and Removing Duplicates, Fixing Noisy Labels, and Handling Missing Values in a Real Dataset | Completed
Video | Hands-On: Tokenization Deep Dive: BPE, WordPiece, and SentencePiece Applied — Tokenizing a Custom Corpus and Inspecting Token Vocabularies, Splitting | Completed
Reading | Data Engineering Best Practices for Fine-Tuning Pipelines
Ungraded Assignment | Practice Knowledge Check: Dataset Cleaning, Tokenization, and Splitting
Lesson 3.3: Evaluation Metrics and Baseline Assessment
Video | Choosing the Right Evaluation Metric: Accuracy, F1, BLEU, ROUGE, Perplexity — What Each Measures, When It Misleads, and How to Report Correctly
Video | Hands-On: Evaluation Metrics Implementation Lab: Computing F1, BLEU, and ROUGE from Scratch and with HuggingFace evaluate | Completed
Video | Hands-On: Zero-Shot Baseline Lab: Running a Pretrained Model Without Fine-Tuning and Recording Baseline Scores for Future Comparison | Completed
Reading | Evaluation Frameworks for Transfer Learning and Fine-Tuning
Ungraded Assignment | Practice Knowledge Check: Evaluation Metrics and Baseline Assessment
Graded Assignment | Knowledge Check: Task Formulation and Dataset Preparation
MODULE 4: Transformer Architectures and Model Selection
Lesson 4.1: Transformer Architecture Deep Dive
Video | Self-Attention and Multi-Head Attention Explained | Completed | Completed
Video | Hands-On: Self-Attention from Scratch: Computing Query-Key-Value Operations in Python — No Black Box, Every Matrix Multiplication Explained | Completed
Video | Hands-On: Transformer Inference Lab: Running Encoder-Only (BERT), Decoder-Only (GPT-2), and Encoder-Decoder (T5) Models — Observing Input/Output Differences | Completed
Ungraded Assignment | Practice Knowledge Check: Transformer Architecture Fundamentals
Lesson 4.2: Foundation Models, Model Families, and Scaling Laws
Video | Model Architectures: Encoder-only, decoder-only, encoder-decoder | Completed | Completed
Video | Hands-On: Model Family Overview: BERT, GPT-2, T5, and DistilBERT
Video | Hands-On: Model Family Deep Dive: RoBERTa, DistilBERT, GPT-2, T5, LLaMA — Architecture Differences, Parameter Counts, and Benchmark Scores Side by Side | Completed
Video | Hands-On: Navigating Hugging Face Hub for Model Selection | Completed
Reading | Scaling Trends and Emergent Abilities in Large Language Models
Reading | Modern Transformer Families and Their Evolution
Ungraded Assignment | Practice Knowledge Check: Foundation Models and Scaling Laws
Lesson 4.3: Model Selection and End-to-End Baseline Pipeline
Video | How to Read a Model Card: Licenses, Benchmarks, and Limitations
Video | Hands-On: Comparing Pretrained Checkpoints: Size, Speed, and Task Fit
Video | Model Selection Framework: Task Type, Dataset Size, Inference Latency Budget, License Requirements, and Hardware Constraints — A Decision Checklist
Video | Hands-On: End-to-End Pipeline Lab: Task Definition → Dataset Preparation → Tokenization → Zero-Shot Baseline → Model Selection — Complete Walkthrough
Video | Hands-On: Head-to-Head Model Evaluation Lab: Running 3 Candidate Checkpoints on Your Prepared Dataset and Comparing Baseline Accuracy, Speed, and Memory | Not Started
Reading | Model Selection Best Practices and Decision Guide for Transfer Learning
Ungraded Assignment | Practice Knowledge Check: Model Selection and Pipeline Assembly
Graded Assignment | Knowledge Check: Transformer Architectures and Model Selection

## Copy of Foundations of Transfer
Artifact | Video Name | Development Status | Recording Status | Drive upload | Reviewer | Review | Planned Date | Completion Date | Final Review on LMS | Remarks
MODULE 1: Python and Machine Learning Fundamentals
Video | Course Introduction |  |  | FALSE |  | FALSE
Reading | Course Syllabus/ overview |  |  | FALSE |  | FALSE
Video | Python: Backbone of Machine Learning | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Setting Up VS Code | Completed | Completed | TRUE |  | FALSE
Reading | Python ML Environment Setup Guide: Conda, pip, and Jupyter Best Practices | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Python Fundamentals for Machine Learning | Completed | Completed | TRUE |  | FALSE
Video | Preparing Data for Machine Learning | Completed | Completed | FALSE |  | FALSE
Video | Hands On: NumPy Arrays and Vectorized Operations | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Pandas for ML Data Handling (attach iris.csv dataset) | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Data Visualization with Matplotlib and Seaborn | Completed | Completed | FALSE |  | FALSE
Reading | NumPy and Pandas Reference Guide for Machine Learning Practitioners | Completed | Completed | FALSE |  | FALSE
Ungraded Assignment | Practice Knowledge Check | Completed |  | FALSE |  | FALSE
Video | Decoding Machine Learning: Core Concepts and Insights | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Building Your First Machine Learning Model | Completed | Completed | TRUE
Video | Hands-On Evaluation of Machine Learning Models | Completed | Completed | TRUE
Reading | Core Machine Learning Concepts: A Practitioner's Reference | Completed | Completed
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Python and Machine Learning Fundamentals
MODULE 2: Neural Networks and Transfer Learning Principles
Video | How Neural Networks Learn | Completed | Completed | TRUE
Video | Neural Network Training Pipelines | Completed | Completed | TRUE
Video | Hands-On: Building a Neural Network using NumPy | Completed | Completed | TRUE | [5 empty] | Y
Reading | Neural Networks: From Perceptrons to Deep Learning | Completed | Completed
Video | Convolutional Neural Networks Architecture Basics | Completed | Completed
Video | Hands-On: CNN Feature Visualization Lab | Completed | Completed
Reading | Deep Learning and Feature Hierarchies Reference | Completed | Completed
Ungraded Assignment | Practice Knowledge Check
Video | Transfer Learning: The Foundation of Modern AI | In Progress |  | FALSE | FALSE | FALSE
Video | Hands-On: Transfer vs Training from Scratch | In Progress
Video | Hands-On: Choosing the Right Transfer Strategy | Completed
Reading | Choosing correct model (IMP) | Completed | Completed
Reading | Transfer Learning Strategies and Use Cases: A Practitioner's Framework | Completed | Completed
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Neural Networks and Transfer Learning Principles
MODULE 3: Transformer Fundamentals and Architecture
Video | Self-Attention and Multi-Head Attention Explained | Completed
Video | Hands-On: Self-Attention from Scratch | Completed
Video | Encoder and Decoder Architecture
Reading | Modern Transformer Families and Their Evolution | Completed | Completed
Ungraded Assignment | Practice Knowledge Check:
Roleplay
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Transformer Fundamentals and Architecture
Video

## Fine-Tuning and Adaptation Tech
| Video Name | Development Status | Recording Status | Drive upload | Reviewer | Review | Planned Date | Completion Date | Final Review on LMS | Remarks
MODULE 1: Model Selection, Data Preparation, and Baselines
Video | Course Introduction |  |  | FALSE |  | FALSE
Reading | Course Syllabus/ overview |  |  | FALSE |  | FALSE
Video | Data Engineering for Fine-Tuning: Quality, Noise, Tokenization, and Splitting | Completed | Completed | TRUE |  | FALSE
Video | Hands-on: Dataset Cleaning and Preparation | Completed | Completed | TRUE |  | FALSE
Video | Text Tokenization for Modern NLP Pipelines |  |  | FALSE |  | FALSE
Reading | Characteristics of High-Quality Fine-Tuning Datasets | Completed | Completed | FALSE |  | FALSE
Video | Task Formulation in machine learning | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Business Problem to ML Task Formulation | Completed | Completed | FALSE |  | FALSE
Ungraded Assignment | Practice Knowledge Check | Completed |  | FALSE |  | FALSE
Video | Hands-On: Label Engineering for Fine-Tuning | Completed | Completed | TRUE |  | FALSE
Reading | Designing Effective Training Examples for Fine-Tuning | Completed | Completed | FALSE |  | FALSE
Video | Hands-On: Hugging Face Model Selection | Completed | Completed | FALSE |  | FALSE
Reading | Fine-Tuning Readiness Checklist | Completed | Completed | FALSE |  | FALSE
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Model Selection, Data Preparation, and Baselines
MODULE 2: Supervised Fine-Tuning Workflows
Video | The Supervised Fine-Tuning Pipeline | Completed | Completed | TRUE
Reading | Understanding Training Dynamics in Large Language Models | Completed | Completed | TRUE | [5 empty] | Y
Video | Training Stability in Modern Fine-Tuning
Video | Learning Rate Schedulers Lab: Linear, Cosine, and Cyclical Comparison | Completed | Completed
Video | Gradient Accumulation and Training Stability | Completed | Completed
Reading | Hyperparameter Trade-offs in Fine-Tuning | Completed | Completed
Ungraded Assignment | Practice Knowledge Check: Supervised Fine-Tuning Workflows
Video | Instruction Fine-Tuning: Datasets, Templates, and Loss Masking | In Progress |  | FALSE | FALSE | FALSE
Video | Hands-On: End-to-End Instruction Fine-Tuning | In Progress
Reading | Common Fine-Tuning Failures and Troubleshooting | Completed | Completed
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Supervised Fine-Tuning Workflows
MODULE 3: Evaluation, Error Analysis, and Parameter-Efficient Fine-Tuning
Video | Choosing the Right Evaluation Metric: Accuracy, F1, BLEU, ROUGE, and Perplexity | Completed
Video | BERT Metrics and Error Analysis | Completed
Reading | Designing Reliable Evaluation Pipelines for Fine-Tuned Models | Completed | Completed
Video | LoRA Explained: Low-Rank Matrix Decomposition, Rank, Alpha, and Adaptation Mechanics | Completed | Completed
Reading | Choosing Between Full Fine-Tuning and PEFT Methods | Completed | Completed
Reading | From Fine-Tuning to Production: What Comes Next? | Completed | Completed
Ungraded Assignment | Practice Knowledge Check: Evaluation, Error Analysis, and Parameter-Efficient Fine-Tuning
Roleplay
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Evaluation, Error Analysis, and Parameter-Efficient Fine-Tuning
Video

## Deploying Fine-Tuned AI Models
| Video Name | Development Status | Recording Status | Drive upload | Reviewer | Review | Planned Date | Completion Date | Final Review on LMS | Remarks
MODULE 1: Practical Foundations for AI Model Deployment
Video | Course Introduction |  |  | FALSE |  | FALSE
Reading | From Fine-Tuning to Production AI Systems |  |  | FALSE |  | FALSE
Video | Hands-On Neural Network Training with PyTorch | Completed | Completed | TRUE |  | FALSE
Video | Dropout and Weight Decay Techniques |  |  | FALSE |  | FALSE
Video | RMSProp and Adam Optimizers | Completed | Completed | TRUE |  | FALSE
Video | Hands-On: Optimizer Performance Comparison |  |  | FALSE |  | FALSE
Reading | PyTorch and Transformer Inference Essentials | Completed | Completed | FALSE |  | FALSE
Video | Understanding Model Compression | Completed | Completed | TRUE |  | FALSE
Reading | Model Compression Techniques for Efficient AI |  |  | FALSE |  | FALSE
Ungraded Assignment | Practice Knowledge Check | Completed |  | FALSE |  | FALSE
Dialogue
Reading | Module Summary
Graded Assignment
MODULE 2: Responsible AI and Model Evaluation
Video | Sources of Bias in Fine-Tuned Models: Data Bias, Label Bias, and Aggregation Bias | Completed | Completed | TRUE
Video | Hands-On Fairness Metrics with Fairlearn | Completed | Completed | TRUE | [5 empty] | Y
Video | Bias Mitigation Strategies
Video | Responsible AI: Core Concepts and Lifecycle | Completed | Completed
Reading | Responsible AI Principles for Fine-Tuned Models | Completed | Completed
Video | AI Transparency and Model Cards | Completed | Completed
Reading | Model Documentation and AI Governance
Ungraded Assignment
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Responsible AI and Model Evaluation
MODULE 3: Serving, Deploying, and Monitoring Fine-Tuned Models
Video | Model Serving Architectures | Completed
Video | Hands-On FastAPI Inference Endpoint | Completed
Video | Latency, Throughput, and Cost Optimization for ML Inference | Completed | Completed
Reading | Best Practices for Serving AI Models | Completed | Completed
Video | Containerization for AI: Why Docker, How Images Work, and What Gets Packaged | Completed | Completed
Reading | Deploying AI Models with Docker and the Cloud
Reading | Securing AI Inference Endpoints for Production
Video | Modern AI Landscape and Governance Challenges
Reading | Experiment Tracking and Production Model Monitoring ¦¦ Testing and Benchmarking Your Inference Endpoint: Response Time and Throughput -- from the perspective of Scaling AI Inference for Production
Roleplay
Dialogue
Reading | Module Summary
Graded Assignment | Knowledge Check: Evaluation, Error Analysis, and Parameter-Efficient Fine-Tuning
Video